## README
Last Update | 2018-10-09
Author | Alex Tran, Melissa Santos, Ryan Gray, Joshua Riley, Krishna Pakalapati
Email | atran049@ucr.edu, msant035@ucr.edu, rgray003@ucr.edu, spaka001@ucr.edu
Description | The software project is based on the social connection app Nearby. Nearby is a smartphone application that enables users to match with each other based on proximity. Our app is similar in that one can connect to other users based on proximity. ​For the most part, we try to keep the functionality and design of our app as close to its inspirations.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Registration | As an unregistered customer who is interested in the app, I want to register an account so that I can login the app | 5 | 1
2 | Secure Log In | As a registered user, I want to login my account with user name and password, and logout my account to end the session | 3 | 2
3 | Change/Update Profile | As a registered user I want to be able to update my profile to accurately describe myself. | 4 | 8
4 | (System) Match Discovery Setting | As a registered user I want to be able to broadcast my current location so I can find users nearby me. | 5 | 5
5 | Message Request | As a user, I want to message any one who is in my contacts | 5 | 4
6 | (User) Discovery | As a registered user I want to people with shared interests to be able to find my profile and connect with me. I want to be able to follow other users’ profiles. | 3 | 6
7 | Security | As a registered user I want to be able to block users that make me feel uncomfortable. I do not want these users to be able to message me or see my profile. | 3 | 9
8 | Feed | As a registered user I want to be able to see the posts of the people that I am following, and the posts of the people that are nearby me | 3 | 7
9 | Messaging | As a registered user, I want to be able to have conversations with people I have followed on the app. | 6 | 3 | You must be able to send messages
10 | Connect with Spotify | As a registered user I want to be able to share my music with people I am talking to. I want to be able to see the music that other users are listening to. | 3 | 10
11 | Connect with Instagram | As a registered user, I want to be able to connect my Instagram pictures to my iLonely account. | 3 | 11
| Total |  | 43

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
| Task 8: Feed | Task 13: Setting up database
Task 5: Message Request | Task 12: Create Website UI (Alex Tran) | Task 1: Registration
| Task 15: Public facing profile UI | Task 2: Secure Log In (Joshua)
| Task 4: (System) Match Discovery Setting | Task 3: Change/update profile (Krishna Pakalapati)
| Task 19: Setup Apache Server | Task 16: User follow list
| Task 18: Integrating Location Services | Task 17: Nearby user list
Task 10: Connect with Spotify | Task 7: Security | Task 14: Password Recovery
Task 11: Connect with Instagram
Task 9: Messaging
Task 18: Integrating Location Services | Task 5: Message Request (Joshua)

## Archives
Sprint ID | Scrum Master | Tasks Completed

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 41 | 0 | 0 | 41 | 41
1 | 41 |  |  |  | 35.875
2 | 41 |  |  |  | 30.75
3 | 41 |  |  |  | 25.625
4 | 41 |  |  |  | 20.5
5 | 41 |  |  |  | 15.375
6 | 41 |  |  |  | 10.25
7 | 41 |  |  |  | 5.125
8 | 41 |  |  |  | 0